## Dashboard
R & D LAB MANAGEMENT DASHBOARD
Materials • Testing • Casting • Resources • Budget
| TOTAL MATERIALS |  | CASTING ACTIVITIES |  | TOTAL TESTS |  |  | CRITICAL MATERIALS |  | TOTAL BUDGET
| 5 |  | 1 |  | 0 |  |  | 3 |  | 48342719
Material To Buy
Budget Status
| S. No | Material |  | Total Budget |  | Utilized |  |  | Balance
| 1 | OPC 53 |  | 48342719 |  | 16800000 |  |  | 31542719
| 2 | Flyash
3
Budget Utilization
34.75%

## Sheet2 (hidden)
34.75%
65.25%
Status | Count | Test | No of Test
Adequate | 6 | Compression | 5
Low | 0 | Flexural Test | 5
Critical | 3 | Flow Test | 5

## Materials & Inventory
Materials & Inventory
| 5 |  |  | 3 |  |  |  | 3 |  |  | 3
8
S.No | Date | Material ID | Material | Category | Supplier | Unit | Opening Stock | Received | Consumed | Closing Stock | Minimum Stock | Required Stock | Order Quantity | Stock Status | Purchase Required | Purchase Priority | Remarks
1 | 2026-09-01 | CEM001 | OPC 53 | Cement | ABC Cement | kg | 100 | 200 | 150 | 150 | 200 | 500 | 350 | Critical | Yes | Urgent | —
2 | 2026-09-01 | CEM002 | Flyash | SCM's | ABC Cement | kg | 100 | 0 | 180 | -80 | 200 | 500 | 580 | Critical | Yes | Urgent | Reorder
3 | 2026-09-01 | CEM003 | GGBS | SCM's | ABC Cement | kg | 370 | 300 | 100 | 570 | 200 | 500 | 0 | Adequate | No | - | —
4 | 2026-09-01 | CEM004 | Super Plastizier | Admixture |  | kg |  |  |  | 0 |  |  | 0 | Adequate | No | -
5 | 2026-09-01 | CEM005 | Steel Fibres |  |  | kg |  |  |  | 0 |  |  | 0 | Adequate | No | -
6 | 2026-09-02 |  | OPC 53 | Cement |  | kg | 150 |  |  | 150 |  |  | 0 | Adequate | No | -
| 2026-09-02 |  | Flyash | SCM's |  | kg | -80 |  |  | -80 |  |  | 80 | Critical | Yes | Urgent
| 2026-09-02 |  | GGBS | SCM's |  | kg | 570 |  |  | 570 |  |  | 0 | Adequate | No | -
| 2026-09-02 |  | Super Plastizier | Admixture |  | kg | 0 |  |  | 0 |  |  | 0 | Adequate | No | -
0
Total Materials
Low Stock
Low Stock
Purchase Required
Urgent Purchases

## Human Resources
Human Resources
S.No | Date | Employee Name | Designation | work Category | Task | Description | Start Time | End Time | Task Status | output/ Result | Issue / Problem | Corrective Action | Supervisor | Remarks | Column1 | Column2 | Column3
1 |  | Dr. Revanth Kumar
2 |  | Dr. Anand Raj
3 |  | Mirityun
4 |  | Neeraj
5 |  | Siva sri
6 |  | Yazhini

## Casting and Testing Activity
MIX ID
S.No | Mix ID | Date | Target Flow (mm) | Target Compressive Strength | Target Flexural Strength | Status | Remarks
Casting And Testing Activity
S.No | Date | Mix ID | Batch No | Target Volume | Actual Volume | Cement | Silica Fume | GGBS | Limestone Powder | Quartz Powder/ Sand | Water | Superplasticizer | SRA | Fibre | Total Binder | W/b Ratio | SP Dosage | Fibre Volume % | Mixing Start Time | Mixing End Time | Humidity | Mixing Duration | Casting Start | Cast Completion | Number Of Specimen | Mould Type | Demoulding Date | Curing Method | Curing Temperature | Responsible ET | Observation | Remarks
1 | 2026-09-07 |  | 1
2 | 2026-09-08 |  | 2
3 | 2026-09-09 |  | 3

## Flow Table Test
Flow Table Test
S.No | Date | Trail ID | Mix ID | Test Standard | Ambient Temperature | UHPC Temperature | d1 (mm) | d2(mm) | D1-D2 | Average speed = (d1+d2)/2 (mm) | Flow Table (mm) | Stabilization Time | Segregation | w/b Ratio | SP Dosage | SRA Dosage | Humidity
1 | 2026-09-01
2 | 2026-09-02
3 | 2026-09-03
4 | 2026-09-04
5 | 2026-09-05

## Compression Test
Compressive Strength Test
S.No | Date | Test ID | Time | Mix ID | Batch ID | Specimen ID | Test Standard | Casting Date | Target Age | Actual Age | Curing Temperature | Testing Temperature | Specimen Type | Nominal Length | Nominal Width | Nominal Height | Measured Length | Mesured Width | Measured Height | Diameter ( cylindrical Specimen ) | Cross sectional Area | Loading Rate (Mpa/s) | Maximum Load (KN) | Failure Type | Faliure Observation | Compressive Strength Mpa | Target Strength Mpa | Remarks
1 | 2026-09-01
2 | 2026-09-02
3 | 2026-09-03
4 | 2026-09-04
5 | 2026-09-05

## Flexural Test
S.No | Date | Test ID | Mix ID | Batch ID | Specimen ID | Test Standard | Test Type | Casting Date | Target Age | Actual Age | Curing Temperature | Testing Temperature | Specimen Type | Notched /Unnotched | Length (mm) | Width (mm) | Height (mm) | Fibre Type | Fibre Length (mm) | Fibre Volume (%) | Notch Depth (mm) | Notch Width (mm) | Support Span (mm) | Loading Direction | Loading Rate (mm/min) | First Crack Load (KN) | First Crack Deflection (mm) | First Crack Stress (Mpa) | Peak Load (KN) | Peak Deflection (mm) | Crack Opening at Peak (mm) | Flexuarl Strength (Mpa) | Residual Strength (Mpa) | Ultimate Deflection (mm) | Toughness (j) | Failure Mode | Remarks
1 | 2026-09-01
2 | 2026-09-02
3 | 2026-09-03
4 | 2026-09-04
5 | 2026-09-05

## Budget
Summary Bangalore Plant Capex for Approval
Cost Head | Basic Amount | GST@18%
Civil Work | 65572779 | 11803100
Plant & Machinery | 73091625 | 13156493
R&D Center | 48342719 | 8701689
Consultancy | 4500000 | 810000
Misc (Store, Labour Qtrs, etc) | 8059200 | 1450656
Sub - Total | 199566323 | 35921938
Land Value | 101250000
Pre Operative Expense | 63600000
Total | 364416323 | 35921938
R&D Center Budget Details
S.No | Lab equipment | No's | Basic |  | gst(18%) | total
1 | Compression Testing M/c-FTM-3000/350kN | 1 | 23717676.4 | 23717676.4 | 4269181.8 | 27986858.15
2 | Sieve Shaker | 1 | 143000 | 143000 | 25740 | 168740
3 | Microwave oven | 1 | 8690 | 8690 | 1564.2 | 10254.2
4 | Mortar Mixer-5 Liter | 1 | 536000 | 536000 | 96480 | 632480
5 | Mortar Mixer-20 Liter | 1 | 409200 | 409200 | 73656 | 482856
6 | Concrete Mixer-Pan | 1 | 205500 | 205500 | 36990 | 242490
7 | Concrete Grinding Machine | 1 | 2035000 | 2035000 | 366300 | 2401300
8 | Automatic Vicat Apparatus | 1 | 629521 | 629521.2 | 113313.8 | 742835.02
9 | V Funnel Apparatus | 1 | 4000 | 4000 | 720 | 4720
10 | Humidity Chamber | 1 | 356366 | 356365.9 | 64145.9 | 420511.76
11 | Curing tank | 1 | 376000 | 376000 | 67680 | 443680
12 | Dust Extraction/Ventilation | 1 | 123000 | 123000 | 22140 | 145140
13 | Plastic Mould-100 x 100 x 100 mm (steeel /Plastic) | 109 | 2600 | 283400 | 51012 | 334412
14 | Dessicator Non-Vacuum Type-200mm dia | 1 | 20378 | 20377.5 | 3668 | 24045.45
15 | Dessicator Vacuum Type-250mm dia | 1 | 25602.5 | 25602.5 | 4608.5 | 30210.95
16 | Vacuum Pump for Dessicator-1/4 HP | 1 | 21285 | 21285 | 3831.3 | 25116.3
17 | Scoop for soil and Concrete | 1 | 1900 | 1900 | 342 | 2242
18 | Scoop, Stainless Steel-Capacity 2kg. | 1 | 1900 | 1900 | 342 | 2242
19 | Restrained Shrinkage Ring | 1 | 165000 | 165000 | 29700 | 194700
20 | Analytical balance | 1 | 120000 | 120000 | 21600 | 141600
21 | Benchtop balance | 1 | 6300 | 6300 | 1134 | 7434
22 | platform balance | 1 | 22000 | 22000 | 3960 | 25960
23 | Muffle furnace | 1 | 201000 | 201000 | 36180 | 237180
24 | Interior design |  | 5500000 | 5500000 | 990000 | 6490000
25 | Curing Tank ( Heat Cool ) | 2 | 625000 | 1250000 | 225000 | 1475000
26 | ASR Moulds | 9 | 20000 | 180000 | 32400 | 212400
| Total |  |  | 36342718.5 | 6541689.3 | 42884407.83

## SCM
SCM Equipments and Instruments
S.No | Item Code | Item Description | HSN | Supplier / Vendor | Delivery Date | Qty | UOM | Rate (₹) | Tax | Purchase Req. | Line Item | Amount (₹) | PO No. | Received Qty | Pending Qty | Actual Delivery Date | Purchase Status
1 | 8507145 | PVC Cube Mould – 50 × 50 × 50 | 39269099 | — | 2026-08-09 | 55 | NOS | 375 | IGST 18% | 230000339 | 1/420 | 20625 | — | — | — | — | Ordered
2 | 8507144 | Plastic Mould – 100 × 100 × 100 mm | 39269099 | — | 2026-08-09 | 55 | NOS | 625 | IGST 18% | 230000339 | 1/410 | 34375 | — | — | — | — | Ordered
3 | 8507150 | Beam Mould – 100 × 100 × 500 mm | 84806000 | — | 2026-08-09 | 3 | NOS | 3700 | IGST 18% | 230000339 | 1/460 | 11100 | — | — | — | — | Ordered
4 | 8507146 | Cube Mould – 40 × 40 × 160 | 84806000 | — | 2026-08-09 | 3 | NOS | 2700 | IGST 18% | 230000339 | 1/430 | 8100 | — | — | — | — | Ordered
5 | — | Twin Shaft Mixer – UHPC Purpose Operated through Servo Motor | — | BHS / Elba | 2026-09-30 | 1 | NOS | — | — | 2300003390 | 10 | 1600000 | 3500003227 | — | — | — | PO Released
6 | — | Compression Testing Machine | — | KAIZEN | 2026-08-20 | 1 | NOS | — | — | 2300003390 | 20 | 495000 | 3500003230 | — | — | — | PO Released
7 | — | Compression Testing Machine – Flexure Option / Servo Valve | — | Controls / Testing | 2026-12-25 | 1 | NOS | — | — | 2300003390 | — | — | — | — | — | — | In Approval
8 | — | Muffle Furnace | — | Srintha Scientific | — | 1 | NOS | — | — | 2300003501 | 10 | 195000 | — | — | — | — | Revised PR Pending
9 | — | Vibro Sieve Shaker – Sand Segregation | — | JS Vibro | — | 1 | NOS | — | — | 2300003391 | 20 | 130000 | — | — | — | — | In Audit
10 | — | Microwave Oven | — | Moglix / LG | — | 1 | NOS | — | — | 2300003391 | 30 | 7900 | — | — | — | — | Revised PR Pending
11 | — | Hot Air Oven | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 40 | 43650 | 3500003266 | — | — | — | PO Released
12 | — | Pycnometer Bottles – Binders and Aggregates | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 50 | 610 | 3500003266 | — | — | — | PO Released
13 | — | Sieve Brass Frame 20 cm × 4.75 mm | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 60 | 675 | 3500003266 | — | — | — | PO Released
14 | — | Sieve Brass Frame 20 cm × 2.36 mm | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 70 | 675 | 3500003266 | — | — | — | PO Released
15 | — | Sieve Brass Frame 20 cm × 1.18 mm | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 80 | 675 | 3500003266 | — | — | — | PO Released
16 | — | Sieve Brass Frame 20 cm × 600 microns | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 90 | 675 | 3500003266 | — | — | — | PO Released
17 | — | Sieve Brass Frame 20 cm × 300 microns | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 100 | 675 | 3500003266 | — | — | — | PO Released
18 | — | Sieve Brass Frame 20 cm × 150 microns | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 110 | 675 | 3500003266 | — | — | — | PO Released
19 | — | Sieve Brass Frame 20 cm × 75 microns | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 120 | 765 | 3500003266 | — | — | — | PO Released
20 | — | Sieve Brass Frame 20 cm × 45 microns | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 130 | 1350 | 3500003266 | — | — | — | PO Released
21 | — | Pan and Cover for 20 cm Sieves | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 140 | 675 | 3500003266 | — | — | — | PO Released
22 | — | Mortar Mixer – 5 Liter | — | Hobart | 2026-09-30 | 1 | NOS | — | — | 2300003391 | 150 | 500000 | — | — | — | — | Commercial Negotiation
23 | — | Mortar Mixer – 20 Liter | — | Mecons | 2026-10-30 | 1 | NOS | — | — | 2300003391 | 160 | 372000 | — | — | — | — | In Approval
24 | — | Concrete Grinding Machine | — | U Test | 2026-11-15 | 1 | NOS | — | — | 2300003391 | 180 | — | — | — | — | — | Commercial Negotiation
25 | — | Automatic Vicat Apparatus | — | Chirayu / Controls | 2026-09-15 | 1 | NOS | — | — | 2300003391 | 190 | 572292 | — | — | — | — | In Approval
26 | — | Slump Test Accessories | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 200 | 2200 | 3500003266 | — | — | — | PO Released
27 | — | Mortar Flow Table Accessories | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 210 | 13050 | 3500003266 | — | — | — | PO Released
28 | — | J Ring Apparatus | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 230 | 9450 | 3500003266 | — | — | — | PO Released
29 | — | L Box Apparatus | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 240 | 10350 | 3500003266 | — | — | — | PO Released
30 | — | U Box Test Apparatus | — | Sai Krishna | 2026-08-11 | 1 | NOS | — | — | 2300003391 | 250 | 9800 | 3500003266 | — | — | — | PO Released